ENVELOPE B

FINANCIAL PROPOSAL

Cloud-Native Application Orchestration & Deployment

Submitted To

DESC Digital Innovation Center, Mardan

Tender Reference: DESC-MRD-2026-CNC-088

Contract Duration: 1 Year (12 Months) Managed Service

Submitted By

Team DeployX

Mardan, Khyber Pakhtunkhwa, Pakistan

| Team Leader: | Nasrullah Khan |
| --- | --- |
| Team Members: | Tauseef Mushtaq, Mustafa Khan, Faryal Khan |
| Faculty Supervisors: | Sir Rafid Imran (TL), Sir Sarwer (PM), Sir Naveed Khan (PM) |
| Submission Date: | 14 June 2026 |
| Currency: | Pakistani Rupees (PKR) |
| Exchange Rate: | 1 USD ≈ PKR 280 (mid-2026 estimate) |

THIS DOCUMENT IS CONFIDENTIAL AND INTENDED SOLELY FOR THE PROCUREMENT / EVALUATION COMMITTEE OF DESC DIGITAL INNOVATION CENTER.

Letter of Transmittal — Financial Proposal

14 June 2026

The Director General

DESC Digital Innovation Center

Mardan, Khyber Pakhtunkhwa, Pakistan

Subject: Submission of Financial Proposal (Envelope B) — Tender Reference DESC-MRD-2026-CNC-088

Dear Sir / Madam,

Team DeployX is pleased to submit this Financial Proposal for the Cloud-Native Application Orchestration and Deployment of the DESC citizen portal. This document constitutes Envelope B of our two-envelope submission, as required under the RFP.

All prices are quoted in Pakistani Rupees (PKR) and are inclusive of all applicable taxes unless stated otherwise. AWS cloud infrastructure costs are based on the ap-south-1 (Mumbai) region at an assumed exchange rate of PKR 280 per USD. Actual cloud costs will be invoiced at actuals and reconciled monthly with supporting AWS billing statements.

This proposal covers the following four cost categories:

- One-time setup and development fee — covering infrastructure setup, application deployment, CI/CD, monitoring, security, and full handover across Phases 1 to 5

- Team salaries — monthly compensation for all four engineers for the full 12-month engagement, billed as part of the managed service retainer

- Monthly managed service retainer — covering ongoing operations, maintenance, reporting, security audits, and support

- AWS cloud infrastructure — estimated monthly cloud costs for running the platform in production on Amazon Web Services

- A 10% contingency reserve for unforeseen technical requirements or approved scope adjustments

We confirm that this Financial Proposal is valid for ninety (90) days from the submission date and that all prices are fixed for the duration of the contract unless a formal written change request is agreed between both parties.

Yours sincerely,

Nasrullah Khan

Team Leader — Team DeployX

Mardan, KPK, Pakistan

Table of Contents

Letter of Transmittal	2

1.   Pricing Summary	4

2.   Phase-by-Phase Cost Breakdown	5

3.   One-Time Setup Costs — Detailed	6

4.   Team Salaries & Compensation	7

5.   Monthly Managed Service Retainer	8

6.   AWS Cloud Infrastructure Costs	9

7.   12-Month Total Cost Summary	10

8.   Cost Justification	11

9.   Payment Terms and Schedule	12

10.   Terms, Conditions & Assumptions	13

11.   Declaration and Signatures	14

1.  Pricing Summary

This section gives a top-level view of the total contract value. All detailed breakdowns are in the sections that follow.

| Cost Component | Amount (PKR) |
| --- | --- |
| One-time setup & development fee (Phases 1–5) | PKR 1,140,000 |
| Team salaries × 12 months (PKR 325,000/month) | PKR 3,900,000 |
| Monthly operations retainer × 12 months (PKR 70,000/month) | PKR 840,000 |
| AWS cloud infrastructure (estimated) × 12 months | PKR 898,968 |
| Sub-total (before contingency) | PKR 6,778,968 |
| Contingency reserve (10%) | PKR 677,897 |
| TOTAL CONTRACT VALUE — 12 MONTHS | PKR 7,456,865 |

Monthly equivalent (total ÷ 12):  PKR 621,405 per month

In words:  Pakistani Rupees Seventy-Five Lakh Twenty-Two Thousand Eight Hundred and Sixty-Five Only

Note: AWS cloud costs are estimates based on ap-south-1 (Mumbai) pricing at PKR 280 per USD. Actual costs are billed at actuals and reconciled monthly with supporting AWS billing statements. Any projected overage above 10% of the monthly estimate will be flagged to DESC before being incurred.

2.  Phase-by-Phase Cost Breakdown

The one-time setup fee is distributed across the five delivery phases. Phase 6 (ongoing managed operations) is a recurring monthly cost for the remainder of the contract.

| Phase | Timeline | Cost (PKR) | % of Setup Budget | Payment Trigger |
| --- | --- | --- | --- | --- |
| Phase 1 — Infrastructure Setup | Weeks 1–2 | PKR 390,000 | 34.2% | DESC sign-off |
| Phase 2 — Application Migration | Weeks 3–4 | PKR 310,000 | 27.2% | DESC sign-off |
| Phase 3 — CI/CD Automation | Weeks 5–6 | PKR 130,000 | 11.4% | DESC sign-off |
| Phase 4 — Monitoring Setup | Weeks 7–8 | PKR 75,000 | 6.6% | DESC sign-off |
| Phase 5 — Hardening & Training | Weeks 9–12 | PKR 235,000 | 20.6% | DESC sign-off |
| Phase 6 — Managed Operations | Months 3–12 | PKR 5,638,968 | Recurring | Monthly invoice |
| TOTAL — Setup Phases 1–5 | Weeks 1–12 | PKR 1,140,000 | 100% |  |

2.1  Payment Trigger per Phase

| Phase | Payment Trigger | Amount Due |
| --- | --- | --- |
| Phase 1 — Infrastructure Setup | K8s cluster live, Terraform apply succeeds, CI/CD pipeline green | PKR 390,000 |
| Phase 2 — Application Migration | All pods Running, app accessible via Ingress, data migrated and verified | PKR 310,000 |
| Phase 3 — CI/CD Automation | Zero-downtime deployment demonstrated, pipeline end-to-end verified | PKR 130,000 |
| Phase 4 — Monitoring Setup | Grafana dashboards live, Prometheus scraping, AlertManager alerts firing correctly | PKR 75,000 |
| Phase 5 — Hardening & Training | Security scan clean, load test passed, documentation approved, staff trained | PKR 235,000 (balance of setup fee) |
| Phase 6 — Managed Operations | Invoiced on 1st of each month, payable within 7 working days | PKR 395,000 + AWS actuals / month |

3.  One-Time Setup Costs — Detailed

These costs cover all work required to deliver the complete platform from scratch across Phases 1 through 5. All figures are inclusive of engineer time, tools, and internal testing.

| Work Item | Category | Qty | Unit Rate (PKR) | Total (PKR) |
| --- | --- | --- | --- | --- |
| Project kickoff, stakeholder meetings & requirement finalisation | Project Management | 1 | PKR 45,000 | PKR 45,000 |
| System architecture design, detailed documentation & review | Technical Planning | 1 | PKR 70,000 | PKR 70,000 |
| Docker containerization — all 3 services (multi-stage builds) | DevOps / Containers | 1 | PKR 90,000 | PKR 90,000 |
| Kubernetes cluster provisioning & namespace configuration | DevOps / K8s | 1 | PKR 110,000 | PKR 110,000 |
| Terraform IaC — full 10-resource infrastructure definition | Infrastructure as Code | 1 | PKR 75,000 | PKR 75,000 |
| CI/CD pipeline — GitHub Actions, Docker Hub, rollout automation | DevOps / Automation | 1 | PKR 90,000 | PKR 90,000 |
| Prometheus + Grafana monitoring stack + 3 pre-configured dashboards | Observability | 1 | PKR 75,000 | PKR 75,000 |
| Security hardening — K8s Secrets, JWT, HTTPS, WAF, namespace RBAC | Security | 1 | PKR 60,000 | PKR 60,000 |
| Data migration, database schema setup & initial data seeding | Database / Migration | 1 | PKR 50,000 | PKR 50,000 |
| Backend API — Node.js, Express, MongoDB, JWT auth endpoints | Development | 1 | PKR 120,000 | PKR 120,000 |
| Frontend — React 18, Nginx, responsive UI, full API integration | Development | 1 | PKR 100,000 | PKR 100,000 |
| Nginx reverse proxy, Ingress controller, routing & CORS setup | Networking | 1 | PKR 40,000 | PKR 40,000 |
| Health probes, readiness checks, rolling update strategy config | K8s Configuration | 1 | PKR 40,000 | PKR 40,000 |
| Load testing, performance tuning & stress testing | QA / Testing | 1 | PKR 45,000 | PKR 45,000 |
| Full technical documentation — handover package | Documentation | 1 | PKR 55,000 | PKR 55,000 |
| DESC IT staff training — 2 formal sessions | Training | 2 | PKR 25,000 | PKR 50,000 |
| Live demonstration preparation, dry run & rehearsal | Demo / Delivery | 1 | PKR 25,000 | PKR 25,000 |
| TOTAL ONE-TIME SETUP FEE |  |  |  | PKR 1,140,000 |

Note: Unit rates are based on market rates for junior-to-mid-level engineers and DevOps professionals in Khyber Pakhtunkhwa as of 2026. These rates reflect the technical complexity of each deliverable, not a flat hourly rate.

4.  Team Salaries & Compensation

Team salaries form the largest portion of the monthly managed service retainer. All four engineers are engaged full-time on this contract for the 12-month duration. The salaries below reflect market-competitive rates for their roles and experience levels in Khyber Pakhtunkhwa.

4.1  Monthly Salary Schedule

| Name | Role | Engagement | Monthly Salary (PKR) | Annual Total (PKR) |
| --- | --- | --- | --- | --- |
| Nasrullah Khan | Team Lead & Cloud Architect | Full-time | PKR 95,000 | PKR 1,140,000 |
| Tauseef Mushtaq | DevOps Engineer | Full-time | PKR 85,000 | PKR 1,020,000 |
| Mustafa Khan | Backend Developer | Full-time | PKR 75,000 | PKR 900,000 |
| Faryal Khan | Frontend Developer | Full-time | PKR 70,000 | PKR 840,000 |
| TOTAL MONTHLY SALARY COST |  |  | PKR 325,000 | PKR 3,900,000 |

4.2  Salary Justification

The salaries above are benchmarked against market rates for DevOps, backend, and frontend engineers in KPK. For reference:

| Role | Our Rate (PKR/mo) | KPK Market Range (PKR/mo) | Islamabad Market Range (PKR/mo) |
| --- | --- | --- | --- |
| DevOps Engineer | PKR 85,000 | PKR 70,000–100,000 | PKR 120,000–200,000 |
| Backend Developer | PKR 75,000 | PKR 60,000–90,000 | PKR 100,000–160,000 |
| Frontend Developer | PKR 70,000 | PKR 55,000–85,000 | PKR 90,000–150,000 |
| Team Lead / Architect | PKR 95,000 | PKR 80,000–120,000 | PKR 150,000–250,000 |

Our rates are within the mid-range for KPK and well below Islamabad/Lahore market rates. This represents good value for DESC given the technical depth of the work being delivered.

4.3  Full-Time Commitment

- All four engineers are dedicated to this contract for the full 12-month period

- No engineer will be shared across multiple contracts without prior written consent from DESC

- If a team member leaves during the contract, a replacement of equivalent qualification will be onboarded within 30 days at no additional cost to DESC

- Faculty supervisors (Sir Rafid Imran, Sir Sarwer, Sir Naveed Khan) provide oversight and technical governance — their time is not billed to the contract

5.  Monthly Managed Service Retainer

The monthly retainer covers two components: team salaries (Section 4) and operational activities. This section details the operational cost component. Both are billed together as the monthly retainer.

5.1  Monthly Retainer Structure

| Component | Monthly Amount (PKR) | Annual Amount (PKR) |
| --- | --- | --- |
| Team salaries (4 engineers — detailed in Section 4) | PKR 325,000 | PKR 3,900,000 |
| Operations, maintenance & support (detailed below) | PKR 70,000 | PKR 840,000 |

| Component | Amount (PKR) |
| --- | --- |
| TOTAL MONTHLY RETAINER | PKR 395,000 |
| TOTAL ANNUAL RETAINER (× 12 months) | PKR 4,740,000 |

5.2  Operational Activities — Monthly Breakdown

| Operations Item | Category | Qty/Hrs | Rate (PKR) | Monthly (PKR) |
| --- | --- | --- | --- | --- |
| 24/7 cluster monitoring, health checks & incident response | Operations | 1 | PKR 10,000 | PKR 10,000 |
| Software updates — K8s, Docker images, OS patches, dependencies | Maintenance | 1 | PKR 8,000 | PKR 8,000 |
| CI/CD pipeline maintenance, improvements & rollback management | DevOps | 1 | PKR 8,000 | PKR 8,000 |
| Monthly security audit, vulnerability scanning & patch management | Security | 1 | PKR 8,000 | PKR 8,000 |
| Grafana dashboard updates, alerting rules & threshold tuning | Observability | 1 | PKR 6,000 | PKR 6,000 |
| Monthly operations report — preparation, review & DESC submission | Reporting | 1 | PKR 6,000 | PKR 6,000 |
| Database backup verification, integrity checks & recovery drills | Database | 1 | PKR 6,000 | PKR 6,000 |
| Minor feature requests & bug fixes (up to 10 hrs/month) | Development | 10 | PKR 1,500 | PKR 15,000 |
| Emergency on-call retainer & out-of-hours critical support | Support | 1 | PKR 3,000 | PKR 3,000 |
| MONTHLY OPERATIONS TOTAL |  |  |  | PKR 70,000 |

5.3  What Is Covered

- Up to 10 hours of minor development work per month (bug fixes, small improvements). Hours above this are billed at PKR 1,800/hour with prior DESC approval.

- 24/7 on-call availability for P1 Critical incidents via phone and WhatsApp

- All routine maintenance — Kubernetes version updates, Docker image rebuilds, dependency patches

- Monthly Grafana dashboard review and alerting rule adjustments

- Monthly written operations report submitted to DESC by the 5th of each month

5.4  What Is NOT Covered

- New feature development beyond the original technical scope (quoted separately on request)

- AWS cloud infrastructure costs (invoiced at actuals — see Section 6)

- Work required due to DESC-initiated changes made without coordination with Team DeployX

6.  AWS Cloud Infrastructure Costs

All figures are estimates based on AWS ap-south-1 (Mumbai) region pricing at PKR 280 per USD. The configuration is sized for a production-grade deployment appropriate to the DESC citizen portal's expected traffic and availability requirements.

| AWS Service | Category | Quantity | USD/Month | PKR/Month | PKR/Year |
| --- | --- | --- | --- | --- | --- |
| EKS Cluster (managed control plane) | Compute | 1 cluster | ~$72/mo | PKR 20,160 | PKR 241,920 |
| EC2 t3.small × 2 (frontend node group) | Compute | 2 nodes | ~$30/mo | PKR 8,400 | PKR 100,800 |
| EC2 t3.medium × 2 (backend node group) | Compute | 2 nodes | ~$60/mo | PKR 16,800 | PKR 201,600 |
| MongoDB Atlas M10 cluster (dedicated, 512MB RAM) | Database | 1 cluster | ~$57/mo | PKR 15,960 | PKR 191,520 |
| Amazon S3 — file uploads + static assets (50GB) | Storage | 50 GB | ~$1.15/mo | PKR 322 | PKR 3,864 |
| Application Load Balancer | Networking | 1 ALB | ~$16/mo | PKR 4,480 | PKR 53,760 |
| Amazon CloudFront CDN (100GB transfer) | CDN | 100 GB | ~$8.50/mo | PKR 2,380 | PKR 28,560 |
| Route 53 hosted zone + DNS queries | DNS | 1 zone | ~$0.90/mo | PKR 252 | PKR 3,024 |
| AWS Secrets Manager (5 secrets) | Security | 5 secrets | ~$2/mo | PKR 560 | PKR 6,720 |
| AWS CloudWatch logs + metrics | Monitoring | Est. | ~$5/mo | PKR 1,400 | PKR 16,800 |
| AWS WAF (WebACL + managed rules) | Security | 1 WebACL | ~$6/mo | PKR 1,680 | PKR 20,160 |
| Data transfer out (100GB/month) | Networking | 100 GB | ~$9/mo | PKR 2,520 | PKR 30,240 |
| ESTIMATED AWS MONTHLY TOTAL |  |  |  | PKR 74,914 | PKR 898,968 |

6.1  Cost Control Measures

- Reserved Instances: After 3 months of production usage data, EC2 nodes will be evaluated for 1-year Reserved Instance conversion — saving up to 40% on compute costs. Savings are passed through to DESC.

- AWS Budgets alert: A budget alert is set at 80% of the monthly estimate. No additional spend above the estimate will be incurred without prior written DESC approval.

- S3 Intelligent-Tiering: Automatically moves infrequently accessed uploaded files to cheaper storage tiers at no operational overhead.

- CloudFront caching: Static React assets are served from edge locations, reducing both S3 request costs and load times for citizens across Pakistan.

- MongoDB Atlas monitoring: Atlas built-in performance advisor is used in place of additional paid CloudWatch alarms for database metrics.

6.2  Billing and Reconciliation

- AWS costs are invoiced monthly at actuals, with the AWS billing statement attached as supporting evidence

- Any month where AWS actuals exceed the estimate by more than 10% will be flagged in the monthly operations report with a root cause explanation

- Unused AWS credits or savings from Reserved Instances are applied to the following month's invoice

7.  12-Month Total Cost Summary

7.1  Month-by-Month Cashflow

| Month | Activity | Setup Fee (PKR) | AWS Cost (PKR) | Retainer (PKR) |
| --- | --- | --- | --- | --- |
| Month 1 | Phase 1 + Phase 2 (infrastructure + migration) | PKR 700,000 | PKR 74,914 | — |
| Month 2 | Phase 3 + Phase 4 + Phase 5 (CI/CD + monitoring + hardening) | PKR 440,000 | PKR 74,914 | — |
| Month 3 | Phase 6 begins — managed operations | — | PKR 74,914 | PKR 395,000 |
| Month 4 | Managed operations | — | PKR 74,914 | PKR 395,000 |
| Month 5 | Managed operations | — | PKR 74,914 | PKR 395,000 |
| Month 6 | Managed operations + mid-contract review | — | PKR 74,914 | PKR 395,000 |
| Month 7 | Managed operations | — | PKR 74,914 | PKR 395,000 |
| Month 8 | Managed operations | — | PKR 74,914 | PKR 395,000 |
| Month 9 | Managed operations | — | PKR 74,914 | PKR 395,000 |
| Month 10 | Managed operations | — | PKR 74,914 | PKR 395,000 |
| Month 11 | Managed operations + contract renewal assessment | — | PKR 74,914 | PKR 395,000 |
| Month 12 | Managed operations + final handover documentation | — | PKR 74,914 | PKR 395,000 |
| TOTALS |  | PKR 1,140,000 | PKR 898,968 | PKR 3,950,000 |

7.2  Grand Total

| Component | Amount (PKR) |
| --- | --- |
| One-time setup & development fee (Phases 1–5) | PKR 1,140,000 |
| Team salaries × 12 months (PKR 325,000/month) | PKR 3,900,000 |
| Operations retainer × 12 months (PKR 70,000/month) | PKR 840,000 |
| AWS cloud infrastructure × 12 months (estimated) | PKR 898,968 |
| Sub-total | PKR 6,778,968 |
| Contingency reserve (10% of sub-total) | PKR 677,897 |
| TOTAL CONTRACT VALUE — 12 MONTHS | PKR 7,456,865 |
| Monthly average (total ÷ 12) | PKR 621,405 |

8.  Cost Justification

8.1  Market Rate Comparison

The total contract value of PKR 7,456,865 over 12 months translates to approximately PKR 621,405 per month for a four-person engineering team running a cloud-native platform. The table below benchmarks this against what an equivalent engagement would cost at market rates.

| Engagement Type | Monthly Cost | Annual Cost | Notes |
| --- | --- | --- | --- |
| Team DeployX (this proposal) | PKR 621,405 | PKR 7,456,865 | Includes AWS, all ops, all salaries |
| IT firm in Islamabad (junior) | PKR 700,000+ | PKR 8,400,000+ | Salaries alone at Islamabad rates |
| IT firm in Islamabad (mid-level) | PKR 1,200,000+ | PKR 14,400,000+ | Senior DevOps teams typically cost more |
| Hiring 4 full-time employees | PKR 600,000+ | PKR 7,200,000+ | Does not include cloud infrastructure |
| Freelance DevOps (Upwork/Fiverr) | Variable | Unreliable | No SLA, no team, no accountability |

8.2  What DESC Is Getting

| Value Item | Justification |
| --- | --- |
| A working, deployed system from day one | We have already implemented this stack — DESC is not paying for a learning curve |
| Four dedicated full-time engineers | A complete team covering architecture, DevOps, backend, and frontend under one contract |
| Open-source tools throughout | No licensing fees. Docker, Kubernetes, Terraform, Prometheus, Grafana — all free to use |
| Full documentation and knowledge transfer | DESC's own IT team can maintain the system independently after the contract ends |
| Auto-scaling and self-healing built in | System recovers from failures automatically and scales under load without manual intervention |
| Zero-downtime deployments | DESC never has to schedule a maintenance window to push an update |
| 10% contingency included | Minor scope adjustments are absorbed without a formal change request |
| Monthly reporting included | DESC management receives a written operations report every month |
| Faculty oversight included at no cost | Sir Rafid Imran, Sir Sarwer, and Sir Naveed Khan provide technical governance — not billed |

8.3  Cost Breakdown by Category

| Category | 12-Month Cost (PKR) | % of Grand Total | Notes |
| --- | --- | --- | --- |
| Team salaries | PKR 3,900,000 | 52.3% | Largest component — 4 engineers, 12 months |
| One-time setup fee | PKR 1,140,000 | 15.3% | Paid in first 2 months |
| AWS infrastructure | PKR 898,968 | 12.1% | Billed at actuals monthly |
| Operations retainer | PKR 840,000 | 11.3% | Monitoring, maintenance, reporting |
| Contingency (10%) | PKR 677,897 | 9.1% | Reserve for unforeseen requirements |
| TOTAL | PKR 7,456,865 | 100% |  |

9.  Payment Terms and Schedule

9.1  Payment Schedule

| Payment # | Trigger / Milestone | Amount (PKR) | Due Date |
| --- | --- | --- | --- |
| Payment 1 — 20% | Contract signed + project kickoff confirmed | PKR 1,491,373 | Within 7 days of contract signing |
| Payment 2 | Phase 1 + Phase 2 delivered and accepted by DESC | PKR 700,000 | End of Month 1 |
| Payment 3 | Phase 3 + Phase 4 + Phase 5 delivered and accepted | PKR 440,000 (balance of setup fee) | End of Month 2 |
| Payments 4–13 (monthly) | Monthly managed service retainer (salaries + ops) + AWS actuals | PKR 395,000 + AWS actuals | 1st of each month, Months 3–12 |

9.2  Payment Method

- Bank transfer to Team DeployX nominated bank account (details provided on contract signing)

- Each payment triggers issuance of a formal tax invoice and receipt within 24 hours

- AWS costs are passed through at actuals — the AWS billing statement is attached to each monthly invoice as evidence

- All invoices to be addressed to the DESC Finance Department with reference to tender DESC-MRD-2026-CNC-088

9.3  Late Payment Policy

If a monthly retainer payment is more than 14 working days late, Team DeployX reserves the right to suspend non-critical maintenance activities until payment is received. P1 and P2 incident response will continue during any payment dispute period. Interest on overdue amounts may be charged at 1% per month after 30 days.

9.4  Contract Renewal

At month 11, Team DeployX will submit a contract renewal proposal for the following 12-month period. Salary rates may be adjusted by a maximum of 10% to account for inflation. AWS costs will be rebased to actual usage averages from months 3–11.

10.  Terms, Conditions & Assumptions

10.1  General Terms

- All prices are quoted in Pakistani Rupees (PKR) inclusive of all applicable taxes unless stated otherwise.

- This Financial Proposal is valid for 90 calendar days from the submission date of 14 June 2026.

- All quoted prices are fixed for the duration of the contract. No price increase will be applied mid-contract without a formal written amendment signed by both parties.

- Intellectual property for all custom code written during this engagement transfers to DESC upon receipt of the final payment.

- Open-source tools and libraries remain under their respective licenses as listed in the Technical Proposal (Envelope A, Section 20).

- Team DeployX retains the right to use this project as a portfolio and academic reference unless DESC formally requests confidentiality in writing.

10.2  Assumptions

- AWS cloud costs are estimated at ap-south-1 (Mumbai) pricing at USD 1 = PKR 280. A significant exchange rate movement (above ±15%) may trigger a pricing review with DESC.

- DESC will provide access to required AWS account credentials, GitHub access, and DESC IT environment access within the first 3 working days of contract commencement.

- DESC will designate a technical point of contact with authority to approve deliverables within 2 working days of submission.

- The existing citizen portal codebase will be made available to Team DeployX within 5 working days of contract signing.

- Reserved Instance savings, if adopted after month 3, will be passed through to DESC as a reduction in the following month's AWS invoice.

- The scope of development work is as described in the Technical Proposal (Envelope A). Any new feature requests are out of scope and will be quoted separately.

10.3  Exclusions

- Hardware procurement (servers, networking equipment, UPS systems) — not included

- Physical data centre or co-location facility costs — not included

- End-user training for citizens using the portal — not included

- Custom mobile application development — not included

- Faculty supervisor time (Sir Rafid Imran, Sir Sarwer, Sir Naveed Khan) — provided as academic oversight at no charge to DESC

11.  Declaration and Signatures

We, the undersigned, hereby declare that:

- All pricing information in this Financial Proposal is accurate, complete, and prepared in good faith.

- No pricing information has been shared with or coordinated with any other bidder participating in this tender.

- We accept all terms and conditions set out in RFP DESC-MRD-2026-CNC-088.

- This proposal is valid for ninety (90) calendar days from the submission date.

- We are prepared to sign a formal contract within fourteen (14) days of receiving a Letter of Intent from DESC.

- The faculty supervisors named below have reviewed this proposal and confirm its technical and financial accuracy.

Team DeployX — Members

| Name | Role | Signature | Date |
| --- | --- | --- | --- |
| Nasrullah Khan | Team Leader & Cloud Architect | ___________________ | 14 June 2026 |
| Tauseef Mushtaq | DevOps Engineer | ___________________ | 14 June 2026 |
| Mustafa Khan | Backend Developer | ___________________ | 14 June 2026 |
| Faryal Khan | Frontend Developer | ___________________ | 14 June 2026 |

Official Stamp / Seal

END OF ENVELOPE B — FINANCIAL PROPOSAL  |  Team DeployX  |  DESC-MRD-2026-CNC-088  |  June 2026